## PR Campaign Template
ACTIVITY TYPE | TASK | WHO | DUE | COMPLETE?
PR | Finalise press release |  | 2 months before event
PR/Digital | Build shareable press folder of high resolution images (Google Drive or Dropbox) |  | 2 months before event
PR | pitch to publications with long-lead times (eg. magazines) |  | 1.5 months before event
Digital | Produce and share info pack for artists, communities and stakeholders providing them with the wording and images they need to tell their networks about the event |  | 1 month before event
PR/Digital | Arrange for an event photographer, provide them with a brief and book them in for the day/hours of the event |  | 1 month before event
PR | Distribute press release widely to national and regional press |  | 1 month before event
Digital | Ensure all web pages are updated with accurate details |  | 1 month before event
PR | Follow-ups and ongoing pitching to key journalists |  | 3 weeks before event (and continuing)
PR | Ensure all local and national listings sites and pages have event details |  | 3 weeks before event
PR | Press invites to key journalists |  | 2 weeks before event
PR/Digital | Remind artists, communities and stakeholders to continue sharing about the event |  | 2 weeks before event
PR/Digital | Check in with photographer and ensure they have a clear idea of what is needed on the day |  | 1 week before the event
Event | Event opens
PR | Greet journalists and ensure they have everything they need to experience the event |  | Day of event
PR | Ensure photographer sends pictures to national photo-desks for coverage |  | Day of event
Digital | Campaign evaluation and reporting |  | 1 week after event